## User Story Template
User Story Template
In theory, user stories are basically product features, requirements or tasks that add value to the end customer.
In practice, most Agile Teams use user stories as tasks that reflect what they are trying to accomplish, which of course is directed to meeting a customer need or requirement.
In theory they should be written like this:
As a <user> (who) I want to… <what> so that… <why>
Example: As a front end developer I need to ensure the app is responsive so that it can work on different screen sizes
But using the format above to write user stories, requires more effort and space (which is limited if you're using post-it notes). Plus it can get a bit repetitive and redundant, so…
In practice, most Agile Teams write user stories as short tasks which start with a verb
<verb> and the task that is being performed (written in a short and concise manner)
Example: Ensure the app is responsive so that it can work on different screen sizes
Examples of verbs to start a user story would be:
Create
Develop
Build
Plan
Research
Perform
Test
and so on

## Velocity Chart Template
Velocity Chart Template
Velocity = Total Story Points Delivered over a Sprint
The example below illustrates a basic example of a 4 Sprint Project. Being the Sprints in this case 2 weeks long this is a 2 month project.
It has 15 user stories in total. I've used the name "User Story #" in the essence of time, but you would of course write the actual user story using the format described in the other tab
Assumption: The team discards the user stories which aren't delivered since after discussion they don't consider required any longer. Keep in mind, that if they were required they would be added to another Sprint
Sprint 1 |  | Story Points
User Story 6 |  | 3 |  | Note: this user story wasn't delivered in Sprint 1 since the team didn't have time to complete it
User Story 11 |  | 3
User Story 2 |  | 5
User Story 8 |  | 1
| Total | 12 | Velocity Sprint 1 | 9
Sprint 2
User Story 1 |  | 5
User Story 13 |  | 1
User Story 5 |  | 1
| Total | 7 | Velocity Sprint 2 | 7
Sprint 3
User Story 3 |  | 5
User Story 4 |  | 3
User Story 15 |  | 1
| Total | 9 | Velocity Sprint 3 | 9
Sprint 4
User Story 9 |  | 3 |  | Note: this user story wasn't delivered in Sprint 4 since the team didn't have time to complete it
User Story 7 |  | 5
User Story 14 |  | 3
User Story 10 |  | 1
User Story 12 |  | 1
| Total | 13 | Velocity Sprint 4 | 10
Total Story Points |  | 41 | Average Velocity | 8.75 | Which means that on average the team is delivering 9 story points per Sprint. This is known as the project's Velocity
This is an indication of execution that allows for future planning and workload management.
Velocity Chart
Sprint | Velocity
1 | 9
2 | 7
3 | 9
4 | 10

## Burndown Chart Template
Velocity Chart Template
Velocity = Total Story Points Delivered over a Sprint
The example below illustrates a basic example of a 4 Sprint Project. Being the Sprints in this case 2 weeks long this is a 2 month project.
It has 15 user stories in total. I've used the name "User Story #" in the essence of time, but you would of course write the actual user story using the format described in the other tab
Assumption: The team discards the user stories which aren't delivered since after discussion they don't consider required any longer. Keep in mind, that if they were required they would be added to another Sprint
Sprint 1 |  | Story Points
User Story 6 |  | 3 |  | Note: this user story wasn't delivered in Sprint 1 since the team didn't have time to complete it
User Story 11 |  | 3
User Story 2 |  | 5
User Story 8 |  | 1
| Total | 12 | Velocity Sprint 1 | 9
Sprint 2
User Story 1 |  | 5
User Story 13 |  | 1
User Story 5 |  | 1
| Total | 7 | Velocity Sprint 2 | 7
Sprint 3
User Story 3 |  | 5
User Story 4 |  | 3
User Story 15 |  | 1
| Total | 9 | Velocity Sprint 3 | 9
Sprint 4
User Story 9 |  | 3 |  | Note: this user story wasn't delivered in Sprint 4 since the team didn't have time to complete it
User Story 7 |  | 5
User Story 14 |  | 3
User Story 10 |  | 1
User Story 12 |  | 1
| Total | 13 | Velocity Sprint 4 | 10
Total Story Points |  | 41 | Average Velocity | 8.75 | Which means that on average the team is delivering 9 story points per Sprint. This is known as the project's Velocity
This is an indication of execution that allows for future planning and workload management.
Traditional
Burndown Chart
Sprint | Remaining Story Points
1 | 41
2 | 32
3 | 25
4 | 16
5 | 6
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 41 | 9
2 | 32 | 7
3 | 25 | 9
4 | 16 | 10
5 | 6 | 0
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 41 | 9
2 | 32 | 7
3 | 25 | 9
4 | 16 | 10
5 | 6 | 0