## Burndown Chart Template
Burndown Chart Template
Velocity = Total Story Points Delivered over a Sprint
The example below illustrates a basic example of a 4 Sprint Project. Being the Sprints in this case 2 weeks long this is a 2 month project.
It has 15 user stories in total. I've used the name "User Story #" in the essence of time, but you would of course write the actual user story using the format described in the other tab
Assumption: The team discards the user stories which aren't delivered since after discussion they don't consider required any longer. Keep in mind, that if they were required they would be added to another Sprint
Sprint 1 |  | Story Points
User Story 6 |  | 3 |  | Note: this user story wasn't delivered in Sprint 1 since the team didn't have time to complete it
User Story 11 |  | 3
User Story 2 |  | 5
User Story 8 |  | 1
| Total | 12 | Velocity Sprint 1 | 9
Sprint 2
User Story 1 |  | 5
User Story 13 |  | 1
User Story 5 |  | 1
| Total | 7 | Velocity Sprint 2 | 7
Sprint 3
User Story 3 |  | 5
User Story 4 |  | 3
User Story 15 |  | 1
| Total | 9 | Velocity Sprint 3 | 9
Sprint 4
User Story 9 |  | 3 |  | Note: this user story wasn't delivered in Sprint 4 since the team didn't have time to complete it
User Story 7 |  | 5
User Story 14 |  | 3
User Story 10 |  | 1
User Story 12 |  | 1
| Total | 13 | Velocity Sprint 4 | 10
Total Story Points |  | 41 | Average Velocity | 8.75 | Which means that on average the team is delivering 9 story points per Sprint. This is known as the project's Velocity
This is an indication of execution that allows for future planning and workload management.
Traditional
Burndown Chart
Sprint | Remaining Story Points
1 | 41
2 | 32
3 | 25
4 | 16
5 | 6
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 41 | 9
2 | 32 | 7
3 | 25 | 9
4 | 16 | 10
5 | 6 | 0
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 41 | 9
2 | 32 | 7
3 | 25 | 9
4 | 16 | 10
5 | 6 | 0